## Test Plan
no. | Tasks
NetApp ONTAP
1 | Snapshot existing volumes
2 | Update snapmirror relation at DR
3 | Verify snapshots are existing at DR
4 | FlexClone Snapshots at DR
5 | Verify FlexClone at DR
6 | Map clone LUNs to initiator (for SAN)
7 | Mount junction path for clone NFS volumes (for NAS)
Vmware
SAN
8 | Rescan hba
9 | Verify duplicate signature
10 | Resignature if needed
11 | Mount LUNs to datastores
12 | Verify Datastores
13 | Rescan hba on all ESXi hosts
14 | Scan for target VMX
15 | Register VMX to vSphere
16 | Power on VM following order
17 | Verify VM status
NAS
18 | Mount NFS volumes to datastore on all ESXi hosts
19 | Verify datastores
20 | Scan for target VMX
21 | Register VMX to vSphere
22 | Power on VM following order
23 | Verify VM status

## Cleanup Test Plan
no. | Tasks
Vmware
SAN
1 | Power of all VMs
2 | Unmount SAN datastores
3 | Verify datastores already unmount
NAS
1 | Power of all VMs
2 | Unmount NFS datastores
3 | Verify datastores already unmount
NetApp
SAN
1 | Offline and Delete clone LUNs
2 | Offline and Delete clone Volumes
3 | Delete Snapshot at DC + DR
NAS
1 | Unmount NFS volumes from junction path
2 | Offline Clone NFS Volumes
3 | Delete Snapshot at DC + DR